## Slide 1: Bedside Shift Report Fellowship Project
Chelsea Lowe, MSN, RN
Hopedale Medical Complex

## Slide 2: Bedside Shift Report
Nurse and CNA report at the patient’s bedside
Including the patient in report
Visualizing patient, safety issues and equipment at the beginning of each shift

## Slide 3: Bedside Shift Report
Staff Communication
Patient Safety
Patient Satisfaction

## Slide 4: Implementation Process
Open discussion about the possibility of implementation.
  Discuss with Hospital admin team, ER/charge nurse committee, staff meeting, 1:1 with staff.
Established bedside shift report champions.
  Charge nurse, floor nurse, CNA.

## Slide 5: Implementation Process
Sent out education via powerpoint to all staff.
  Included the specifics of who, what, why, and when.
  Included evidence with studies and articles.
  Included specific HMC examples.
  Included a video example.

## Slide 6: Implementation Process
Consistent with our timeline.
Sent reminders for start date.
Go Live of April 11th.
Monitored implementation through audits and being present for report.

## Slide 7: Bedside Shift Report
Barriers
Gaining buy in
Moving away from the mentality of “We have always done it this way”.
Fear of waking the patients
Successes
Accountability between shifts has improved.
Staff understanding that bedside report is excellent practice
Good catches:
  patient’s alarm was not on, IV not unclamped

## Slide 8: Outcomes to date
Staff is compliant and understands the need.
Several good catches.
Still continue to monitor.
Improved ownership and accountability between the shifts.

## Slide 9: Conclusions
Monitoring the effectiveness of bedside shift report will require continued monitoring of
  Patient satisfaction scores
  Staff rapport
  Patient falls
  Nursing practice

## Slide 10
Questions?